## User stories
Card | Story | Back of the card | Tasks | Status | Estimated Time
Card1 | As a user I want to be able to sign in or sign up to perform the ATM operations. | The app should validate the given username and password. | Create a home flow in which user can register his account which gets saves into file by his username in the directory.Registered user can also go through the same homeMenu flow in order to login with the registerd information. to write the file I've created the method in the controller class. | Done | 2 hour
Card2 | As a user I want to view the balance of my bank account so that I can plan the upcoming ATM operations. | The user needs to be logged in first. •Blance should be displayed. | Created the accountMenu for the user that has sucessfully being login. In which user can view its balance saved in the respective records. To view the menu there is display_account_menu method in the accountMenu. | Done | 2 hour
Card3 | As a user I want to deposit money into my bank account so that I can perform transactions. | The user needs to be logged in first. • The app should display the deposited amount. • The account balance is updated. | In the AccountMenu there is a option avaiable for the user to deposit funds in to the account and which gets saved in to file of the respective user. Information will be modify with new account balance using the method of modifyFile in the account menu class. | Done | 2 Hour 30 Minutes
Card4 | As a user I want to withdraw money from my bank account using ATM so that I save my time for later transactions. | The user needs to be logged in first. • The app displays the balance and asks user to input the amount to be withdrawn. •The app checks if the amount exceeds the available balance • If Yes the app asks the user to enter a new amount.• If the entered amount is less than the available amount, the balance is withdrawn and the new balance is displayed. | In order to withdraw money the just needs to select the withdraw option from the Account menu and if to withdrawed amount is available the user can withdraw the funds otherwise it prompt the user to enter the correct amount with in the provided limit of the account balance. The account balance information will the updated with the modifyFile method in the accountMenu class. | Done | 5 Hour
Card5 | As a user I want to transfer money from my bank account to another account so that I save time and its cost effective. | • the user needs to be logged in first. • the app should check the receivers account and validate it before performing transactions.• The system must update both accounts. | user can transfer money to the other user from selecting the option of transfer money from the accountMenu in which user just have to type the username of person to which he wants to transfer the funds. The provided user name will be chacked whether it exist or not in the account menu selection and then will be transfer to respective user. | Done | 4 hour
Card6 | As a user I want to view the transaction history of my bank account to show a more detailed and recent activities. | The user needs to be logged in first. The app should display the date and time of each individual activity that have been done in the prior period. | Transaction history can also be shown from the account menu. Transaction history gets saved into the file of the user on calling the transaction history the transaction of the respective user can be displayed. It will just display the information from the file of the user read buffer. | Done | 4 hours
Card7 | As a user I want to logout from my bank account so that to end up my ATM session. | The user is logged out from the account | Final option fro the account menu will be logout. It will exit the project and user account will be logged out from the system. | Done | 30 minutes
Card8 | As a user I want to update my account information so I can change my password regularly | The user needs to be loged in. The system must display the user info(full name, user name and password). The user must have an option for updating the user name and the password. The full name is not changeable. If updated The system displays the new account information to user. | User can edit his record from the account menu. By providing the username and password and it will edit the respective information of the respective user. By providing the new username the modifyFile method will edit the information with new information and .move method will change the filename to new name. | Done | 7 hours